## Paperwork_Status_45
Site_ID | LGA | Ward | Land_Title_Status | Environmental_Approval | Traditional_Leader_Consent | LGA_Permit | Community_Hearing_Minutes | Civil_Works_Status | Owner | Last_Update | Notes
NSW-PHASE1-S01 | Lafia | Akun | complete | complete | complete | complete | concluded 2026-09-08 | complete | Ifeanyi Okeke | 2026-09-30T17:00 | Acquired; ready for installation
NSW-PHASE1-S02 | Lafia | Doma | complete | complete | complete | complete | concluded 2026-09-04 | complete | Ifeanyi Okeke | 2026-09-29T11:00 | Acquired; ready for installation
NSW-PHASE1-S03 | Lafia | Akun | in dispute | pending | objection - tradition leader engagement | pending | Oct 10 cancelled, moved to Oct 7 per FC margin note | pending | Chioma Ndukwe | 2026-10-02T15:00 | Objection from Akun CDA; Chief Musa Adamu engagement rescheduled to Oct 7 per Friday Oct 2 phone call. Typed letter Oct 10 date is cancelled per FC margin note.
NSW-PHASE1-S04 | Akwanga | Akwanga Town | complete | complete | complete | complete | concluded 2026-09-12 | complete | Ifeanyi Okeke | 2026-09-25T10:00 | Acquired; ready for installation
NSW-PHASE1-S05 | Akwanga | Gudi | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-28T16:00 | Acquired; ready for installation
NSW-PHASE1-S06 | Akwanga | Nunku | in negotiation | pending | scheduled | pending | scheduled Oct 5 | pending | Ifeanyi Okeke | 2026-09-30T14:00 | Vendor permit delay; LGA permit issue
NSW-PHASE1-S07 | Akwanga | Ningo | complete | in review | complete | complete | scheduled Oct 5 | in progress | Ifeanyi Okeke | 2026-10-03T22:14 | Closure paperwork signed Oct 3 22:00 per NSW-247. Acquired; environmental in review.
NSW-PHASE1-S08 | Akwanga | Andaha | in dispute | pending | objection - women's forum | pending | scheduled Oct 13 | pending | Chioma Ndukwe | 2026-10-01T11:00 | Objection from Andaha Women's Forum (Mrs. Patience Yakubu)
NSW-PHASE1-S09 | Karu | Karu Town | complete | complete | complete | complete | concluded 2026-09-02 | complete | Ifeanyi Okeke | 2026-09-22T09:00 | Acquired; ready for installation
NSW-PHASE1-S10 | Karu | Gitata | in dispute | pending | scheduled | pending | pending | pending | Ifeanyi Okeke | 2026-09-29T13:00 | Land deed dispute with Mararaba boundary
NSW-PHASE1-S11 | Karu | Mararaba | in dispute | pending | objection - tradition leader | pending | scheduled Oct 17 | pending | Chioma Ndukwe | 2026-10-02T09:30 | Objection from Pastor Daniel Ogbu (Mararaba Fellowship); boundary dispute with Gitata
NSW-PHASE1-S12 | Keffi | Keffi Town | complete | complete | complete | complete | concluded 2026-09-09 | complete | Ifeanyi Okeke | 2026-09-26T15:00 | Acquired; ready for installation
NSW-PHASE1-S13 | Keffi | Liman | complete | complete | complete | complete | concluded 2026-09-11 | complete | Ifeanyi Okeke | 2026-09-27T12:00 | Acquired; ready for installation
NSW-PHASE1-S14 | Keffi | Angwa | in dispute | pending | objection - jama'at | pending | scheduled Oct 16 after Asr | pending | Chioma Ndukwe | 2026-10-01T14:00 | Objection from Angwa Jama'at Council (Alhaji Sadiq Ibrahim); mosque proximity
NSW-PHASE1-S15 | Nasarawa | Toto | in dispute | pending | objection - council of elders | pending | scheduled Oct 17 | pending | Chioma Ndukwe | 2026-10-02T16:30 | Objection from Toto Council of Elders (Chief Patrick Audu); burial-ground proximity
NSW-PHASE2-S01 | Lafia | Ward-1 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-02T15:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S02 | Akwanga | Ward-2 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-03T22:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S03 | Karu | Ward-3 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-04T12:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S04 | Keffi | Ward-4 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-05T19:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S05 | Nasarawa | Ward-5 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-06T09:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S06 | Doma | Ward-6 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-07T16:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S07 | Toto | Ward-1 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-08T23:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S08 | Kokona | Ward-2 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-09T13:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S09 | Wamba | Ward-3 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-10T20:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S10 | Awe | Ward-4 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-11T10:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S11 | Lafia | Ward-5 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-12T17:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S12 | Akwanga | Ward-6 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-13T24:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S13 | Karu | Ward-1 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-14T14:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S14 | Keffi | Ward-2 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-15T21:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S15 | Nasarawa | Ward-3 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-16T11:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S16 | Doma | Ward-4 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-17T18:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S17 | Toto | Ward-5 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-18T08:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S18 | Kokona | Ward-6 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-19T15:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S19 | Wamba | Ward-1 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-20T22:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S20 | Awe | Ward-2 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-21T12:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S21 | Lafia | Ward-3 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-22T19:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S22 | Akwanga | Ward-4 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-23T09:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S23 | Karu | Ward-5 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Chinwe Eze | 2026-09-24T16:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S24 | Keffi | Ward-6 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Emeka Adeniyi | 2026-09-25T23:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S25 | Nasarawa | Ward-1 | complete | complete | complete | complete | concluded 2026-09-15 | complete | Ifeanyi Okeke | 2026-09-26T13:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S26 | Doma | Ward-2 | in negotiation | pending | scheduled | pending | scheduled Nov 2 | pending | Chinwe Eze | 2026-09-27T20:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S27 | Toto | Ward-3 | in negotiation | pending | scheduled | pending | scheduled Nov 2 | pending | Emeka Adeniyi | 2026-09-28T10:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S28 | Kokona | Ward-4 | in negotiation | pending | scheduled | pending | scheduled Nov 2 | pending | Ifeanyi Okeke | 2026-09-01T17:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S29 | Wamba | Ward-5 | in negotiation | pending | scheduled | pending | scheduled Nov 2 | pending | Chinwe Eze | 2026-09-02T24:00 | Phase 2 target Dec 11, 2026
NSW-PHASE2-S30 | Awe | Ward-6 | in negotiation | pending | scheduled | pending | scheduled Nov 2 | pending | Emeka Adeniyi | 2026-09-03T14:00 | Phase 2 target Dec 11, 2026