## Manifest_All_80
Line_ID | PO_Number | Project_Label | Item_Description | Item_Category | Quantity | Unit_Price_USD | Line_Total_USD | Vendor | Country_Of_Origin | Logistics_Status | Logistics_Status_Updated | Carrier | Tracking_Number | Expected_Delivery | Actual_Receipt_Date | Notes
VND-2026-Q4-0001 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8001 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0002 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 4 | 2700 | 10800 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8002 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0003 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 5 | 280 | 1400 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8003 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0004 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 2 | 180 | 360 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8004 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0005 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 3 | 70 | 210 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8005 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0006 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 4 | 45 | 180 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8006 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0007 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 5 | 135 | 675 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8007 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0008 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 2 | 410 | 820 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8008 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0009 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 3 | 240 | 720 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8009 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0010 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 4 | 315 | 1260 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8010 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0011 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8011 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0012 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 2 | 2700 | 5400 | Tachyon Networks Nigeria Ltd | China | delivered to site | 2026-09-15 | DHL Express | DHL-NG-4421-8012 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0013 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 3 | 280 | 840 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8013 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0014 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 4 | 180 | 720 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8014 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0015 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 5 | 70 | 350 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8015 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0016 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 2 | 45 | 90 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8016 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0017 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 3 | 135 | 405 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8017 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0018 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 4 | 410 | 1640 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8018 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0019 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 5 | 240 | 1200 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8019 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0020 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 2 | 315 | 630 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8020 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0021 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8021 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0022 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 4 | 2700 | 10800 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8022 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0023 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 5 | 280 | 1400 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8023 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0024 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 2 | 180 | 360 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8024 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0025 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 3 | 70 | 210 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8025 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0026 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 4 | 45 | 180 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8026 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0027 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 5 | 135 | 675 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8027 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0028 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 2 | 410 | 820 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8028 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0029 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 3 | 240 | 720 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8029 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0030 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 4 | 315 | 1260 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8030 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0031 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8031 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0032 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 2 | 2700 | 5400 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8032 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0033 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 3 | 280 | 840 | Tachyon Networks Nigeria Ltd | China | received at warehouse | 2026-09-22 | DHL Express | DHL-NG-4421-8033 | 2026-10-19 | 2026-09-25 | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0034 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 4 | 180 | 720 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8034 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0035 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 5 | 70 | 350 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8035 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0036 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 2 | 45 | 90 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8036 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0037 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 3 | 135 | 405 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8037 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0038 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 4 | 410 | 1640 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8038 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0039 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 5 | 240 | 1200 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8039 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0040 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 2 | 315 | 630 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8040 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0041 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8041 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0042 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 4 | 2700 | 10800 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8042 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0043 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 5 | 280 | 1400 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8043 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0044 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 2 | 180 | 360 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8044 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0045 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 3 | 70 | 210 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8045 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0046 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 4 | 45 | 180 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8046 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0047 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 5 | 135 | 675 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8047 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0048 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 2 | 410 | 820 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8048 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0049 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 3 | 240 | 720 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8049 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0050 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 4 | 315 | 1260 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8050 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0051 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | in transit | 2026-09-28 | DHL Express | DHL-NG-4421-8051 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0052 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 2 | 2700 | 5400 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8052 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0053 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 3 | 280 | 840 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8053 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0054 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 4 | 180 | 720 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8054 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0055 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 5 | 70 | 350 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8055 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0056 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 2 | 45 | 90 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8056 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0057 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 3 | 135 | 405 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8057 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0058 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 4 | 410 | 1640 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8058 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0059 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 5 | 240 | 1200 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8059 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0060 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 2 | 315 | 630 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8060 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0061 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | in customs - delayed | 2026-10-04T03:14:00Z | DHL Express | DHL-NG-4421-8061 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G. Customs hold pending NCC type-approval certificate cross-check.
VND-2026-Q4-0062 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 4 | 2700 | 10800 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8062 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0063 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 5 | 280 | 1400 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8063 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0064 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 2 | 180 | 360 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8064 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0065 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 3 | 70 | 210 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8065 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0066 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 4 | 45 | 180 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8066 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0067 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 5 | 135 | 675 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8067 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0068 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 2 | 410 | 820 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8068 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0069 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 3 | 240 | 720 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8069 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0070 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 4 | 315 | 1260 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8070 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0071 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | 5G NR Massive MIMO radio unit, 64TR ed.2 | Radio unit | 1 | 4000 | 4000 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8071 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0072 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Edge baseband processor BBU-7600 | Baseband | 4 | 2700 | 10800 | Tachyon Networks Nigeria Ltd | China | in customs - delayed | 2026-10-04T03:14:00Z | DHL Express | DHL-NG-4421-8072 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G. Customs hold pending tariff classification dispute.
VND-2026-Q4-0073 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Sector antenna unit | Antenna | 3 | 280 | 840 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8073 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0074 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | DC power supply module | Power | 4 | 180 | 720 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8074 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0075 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | RF feeder cable assembly | Cable | 5 | 70 | 350 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8075 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0076 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Antenna mounting bracket | Mounting | 2 | 45 | 90 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8076 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0077 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Fronthaul optical transceiver | Optical | 3 | 135 | 405 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8077 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0078 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Microwave backhaul module | Backhaul | 4 | 410 | 1640 | Tachyon Networks Nigeria Ltd | China | shipped | 2026-09-30 | DHL Express | DHL-NG-4421-8078 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0079 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | BBU spare board | Spare | 5 | 240 | 1200 | Tachyon Networks Nigeria Ltd | China | pending shipment | 2026-10-02 | DHL Express | DHL-NG-4421-8079 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
VND-2026-Q4-0080 | TCH-PO-2026-019 | LAG-CSTL-PHASE2-Q4 | Radio unit spare board | Spare | 2 | 315 | 630 | Tachyon Networks Nigeria Ltd | China | pending shipment | 2026-10-02 | DHL Express | DHL-NG-4421-8080 | 2026-10-19 |  | Per TCH-PO-2026-019 / PRJ-ABU-5G (Abuja CBD 5G Densification Pilot)
TOTAL

## At_Risk_Detail
Line_ID | Item_Description | Quantity | Unit_USD | Total_USD | Logistics_Status | Logistics_Status_Updated | Carrier | Tracking_Number | Expected_Delivery | Days_Until_Deadline | Action_Required | Vendor_Recommendation
VND-2026-Q4-0061 | 5G NR Massive MIMO radio unit, 64TR ed.2 | 1 | 4000 | 4000 | in customs - delayed | 2026-10-04T03:14:00Z | DHL Express | DHL-NG-4421-8061 | 2026-10-19 | 15 | NCC type-approval certificate cross-check at NCC Type Approval office | Expedite via TCH-EXP-2026-0017 (NGN 75,000 quote attached separately)
VND-2026-Q4-0072 | Edge baseband processor BBU-7600 | 4 | 2700 | 10800 | in customs - delayed | 2026-10-04T03:14:00Z | DHL Express | DHL-NG-4421-8072 | 2026-10-19 | 15 | Tariff classification dispute resolution (HS code 8517 vs 8525) | Expedite via TCH-EXP-2026-0017 (NGN 75,000 quote attached separately)
TOTAL at-risk inventory

## Status_Aggregate
Status | Line count (live) | Line count (baseline) | Delta
delivered to site | 12 | 12 | 0
received at warehouse | 21 | 21 | 0
in transit | 18 | 18 | 0
shipped | 25 | 27 | -2
in customs - delayed | 2 | 0 | 2
pending shipment | 2 | 2 | 0
TOTAL | 80 | 80 | 0